## Timeline
Oregon Real Estate Broker License — Timeline (Oct 12, 2026 → Jan 1, 2027)
Edit the Start / End dates (blue) and Status — the grid on the right updates automatically. Dates are suggested targets; confirm requirements at oregon.gov/rea.
Week starting (Mon)
Task | Type | Start | End | Days | Status | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28
Getting started
Buy The CE Shop Oregon Broker Pre-License course (confirm OREA approval) | Setup | 2026-10-12 | 2026-10-14 | 3 | Not started | 1
Set weekly study schedule (~20 hrs/week) | Setup | 2026-10-12 | 2026-10-18 | 7 | Not started | 1
Pre-license coursework (~150 hrs)
Real estate principles & Oregon law | Course | 2026-10-15 | 2026-11-08 | 25 | Not started | 1 | 1 | 1 | 1
Finance & contracts | Course | 2026-11-09 | 2026-11-22 | 14 | Not started |  |  |  |  | 1 | 1
Oregon practices, agency & property management | Course | 2026-11-23 | 2026-12-06 | 14 | Not started | [6 empty] | 1 | 1
Pass course final exam / get completion certificate | Milestone | 2026-12-07 | 2026-12-09 | 3 | Not started | [8 empty] | 1
State exam
Create PSI account & schedule the exam | Exam | 2026-12-01 | 2026-12-06 | 6 | Not started | [7 empty] | 1
Exam prep: practice tests & weak areas | Exam | 2026-12-07 | 2026-12-20 | 14 | Not started | [8 empty] | 1 | 1
Take the Oregon broker exam (PSI) | Milestone | 2026-12-21 | 2026-12-22 | 2 | Not started | [10 empty] | 1
Licensing & brokerage
Research & interview principal brokers | Career | 2026-11-16 | 2026-12-20 | 35 | Not started | [5 empty] | 1 | 1 | 1 | 1 | 1
Fingerprinting / background check (per OREA instructions) | Licensing | 2026-12-14 | 2026-12-23 | 10 | Not started | [9 empty] | 1 | 1
Apply for broker license in OREA eLicense & pay fee | Licensing | 2026-12-22 | 2026-12-28 | 7 | Not started | [10 empty] | 1 | 1
Sign on with principal broker → license active | Milestone | 2026-12-28 | 2027-01-01 | 5 | Not started | [11 empty] | 1
Legend
Task in progress that week
Milestone
Task marked Done
Blue text = dates you can edit. Status uses a dropdown: Not started / In progress / Done.
0 of 13 tasks done